## Capital Investment Plan
| Beaux Arts Capital Investment Plan [2026 - 2031] - Exhibit A | [5 empty] | Last Update: 7/3/2025 Updated By: James McCarthy / Sue Ann Spens
Ref | Project Name | Project Description | Priority | Planned Year | Estimated Investment | Estimated On-Going Costs | Funding Strategy | Notes
I. Transportation |  |  |  |  | 495000 | 0
1.1 | Overlay SE 104th/28th/105th | Grind and overlay artierial - replace/repair broken curbs and sidewalk |  | 2026 | 250000 |  | Cum Res fund (REET) | INC with COB watermain work??
1.2 | Village wide | Pavement repair - potholes, truck damage and utility cuts |  | 2026 | 20000 |  | Cum Res fund (REET)
1.3 | Overlay 107th AVE SE from SE 28th to SE 29th | Grind and overlay |  | 2027 | 50000 |  | Cum Res fund (REET), Heavy Truck fee
1.3a | 107th Ave SE southern speedhump repair | Grind & resurface speedhump correcting steepness & winter ponding |  | 2026 | 5000 |  | Cum Res fund (REET)
1.3b | 107th & 29th surface repair | Grind & resurface low spot at NE corner of intersection for ponding |  | 2026 | 5000 |  | Cum Res fund (REET)
1.4 | SE 29th Overlay - Phase 3 | SE 29th Street - from 105th Ave SE to street end |  | 2027 | 60000 |  | Cum Res fund (REET)
1.5 | Replace Retention wall on 103 & SE 27th | Replace existing railroad ties that stabilize slope |  | 2028 | 90000 |  | Cum Res fund (REET)
1.6 | Signage replacement | replacement of surface and street signage, and striping |  | 2025 | 15000 |  | Cum Res fund (REET)
II. Stormwater |  |  |  |  | 122000 | 0
2.1 | Storm Water System Improvements (SCMP CIP-14) | Slurry Deposited 10 ft downstream of CB #637 and Hole in the Pipe 31 ft Downstream of CB #637 |  | 2025-2026 | 14000 |  | Cum Res fund (REET)
2.2 | Storm Water System Improvements (SCMP CIP-15 and CIP-8) | Pipe is Cracked 49 ft downstream of CB #674 and Debris 236 ft downstream of CB #674; Debris 46 ft downstream of #662 |  | 2025 | 13000 |  | Cum Res fund (REET)
2.3 | Storm Water System Improvements (SCMP CIP-16) | Pipe is Broken 76-feet Upstream of CB #672 |  | 2025-2026 | 18000 |  | Cum Res fund (REET)
2.4 | Storm Water System Improvements (SCMP CIP-10) | Pipe is Broken between CBs #529 and 543 |  | 2025-2026 | 22000 |  | Cum Res fund (REET)
2.5 | Storm Water System Improvements (SCMP CIP-19) | 107th Ave SE-South of SE 28th Street. Localized Flooding in the Roadway Shoulder |  | 2026 | 14000 |  | Cum Res fund (REET)
2.6 | Storm Water System Improvements (SCMP CIP-13) | Pipe is Broken Between CBs #587 and #595. Pipe is Reverse-Sloped |  | 2025-2026 | 17000 |  | Cum Res fund (REET)
2.7 | Storm Water System Improvements (SCMP CIP-21) | Pipe Between CBs #701 and #704. Pipe is Reverse-Sloped |  | 2025-2026 | 24000 |  | Cum Res fund (REET)
III. Water Department |  |  |  |  | 740000 | 0
3.1 | 104th Water Supply Pipe Replacement (section) | Replace 104th supply line pipe from SE 27th to SE 28th (4" A/C line) |  | 2026 | 350000 |  | Water fund
3.2 | 107th Water Supply Pipe Replacement (section) | Replace 107th supply line pipe from SE 29th to SE 28th (4" A/c line) |  | 2028 | 270000 |  | Water fund
3.3 | SE 29th Water Supply Line | Install new supply line along SE 29th from 103rd Ave SE to South Beach (for water quality improvement) |  | 2028 | 75000 |  | Water fund
3.4 | Well Pump Replacement | Planned pump replacement |  | 2027 | 25000 |  | Water fund
3.5 | Touch up' Exterior Water Tower | Ongoing maintenance |  | 2029 | 15000 |  | Water fund
3.6 | Water Tank Inspection | Interior Water Tower Inspection |  | 2027 | 5000 |  | Water fund
3.7 | Backflow prevention on COB service line | Install DCVA on Bellevue service line on 28th ROW btw 108th and 107th |  | 2027 | 80000 |  | Water fund | For discussion
IV. ROW Improvements |  |  |  |  | 295000 | 0
4.1 | 108th Ave SE Right of Way | Landscape design and implementation of landscaping, including extension of retaining wall |  | 2026-2028 | 125000 |  | Cum Res fund (REET)
4.2 | Glen Path | Enhanced Screening |  | 2025-2026 | 10000 |  | KC Parks Levy
4.3 | East side of 104th-105th thoroughfare | Restore and Plant |  | 2026-2028 | 50000 |  | KC Parks Levy/CUM RES FUND (REET)
4.4 | Irrigation System | Design and implementation of automated irrigation system for town common areas |  | 2026-2028 | 100000 |  | KC Parks Levy/CUM RES FUND (REET)
4.5 | 29th Ave and 106th Corner | Landscape design and implementation of landscaping |  | 2025-2026 | 10000 |  | BAV Parks Dept
4.6 | Improvement of path/stairs between 29th & 30th | Possible path/stair improvements |  | 2025-2027 | 30000 |  | KC Parks Levy
V. Parks and Land Management |  |  |  |  | 85000 | 0
5.1 | Canopy Study | Canopy Study |  | 2025-2026 | 25000 |  | BAV Parks Dept
5.2 | Town Survey | Break the town up into 3 sections: in Upper Village, 2 sections in Lower Village. Also survey town ROW, trees, water and sewer lines using GIS. All results to be shared online for reference, transparency. 5 years project, $15k/year. |  | 2025-2030 | 60000 |  | BAV Parks Dept | 5 years, $15k/year. 1 year done, 4 remaining
Investments Pending Evaluation | [5 empty] | 0
| 104th/105th Traffic Calming | Improvements for 104th/105th for speed and cut through traffic mitigation |  | tbd | tbd
| Pathway Lighting | Design and implementation of landscaping lighting for town paths |  | conceptual | conceptual |  | KC Parks Levy
| Town hall / Community Center | Needs assessment, design, and development of town hall / community center |  | tbd | tbd
| Security System | Design and implementation of security camera system for entrances to town, possibly other key locations |  | conceptual | 15000 |  | Criminal Justice fund | Medina pays approx $3k per camera, annually + $150 installation per camera
| Wellhead Generator | Design generator hookup for wellhead pump and/or permanent backup generator design/installation |  | conceptual | conceptual |  | Water fund
| Hazard Mitigation | Develop plan for protecting urban forest |  | conceptual | conceptual |  | Hazard Mitigation grants?