## Capital Investment Plan
| Beaux Arts Capital Investment Plan [2020 - 2025] - Exhibit A | [6 empty] | Last Update: 7/15/2019 Updated By: Sue Ann Spens
xRef | Project Name | Project Description | Priority | Planned Year | Estimated Investment | Estimated On-Going Costs | Funding Strategy | Notes
I. Transportation |  |  |  |  | 199100 | 0
1.1 | 27th Overlay | SE 27th Street - from 104th (in assoc. w/stormwater) |  | 2021 | 55000 | 0 | Cum Res fund (REET)
1.2 | 102nd Ave SE Overlay | 102nd Ave SE - from SE 28th to street end |  | 2020 | 28600 | 0 | Cum Res fund (REET)
1.3 | SE 28th St. Overlay | SE 28th Street - from 104th Ave SE to 102nd Ave SE |  | 2020 | 35750 | 0 | Cum Res fund (REET)
1.4 | 103rd Overlay | 103rd Ave SE - from SE 28th to SE 27th |  | 2020 | 22000 | 0 | Cum Res fund (REET)
1.5 | 103rd Overlay | 103rd Ave SE - from SE 29th to SE 28th |  | 2021 | 22000 | 0 | Cum Res fund (REET)
1.6 | SE 29th Overlay - Phase 3 | SE 29th Street - from 105th Ave SE to street end |  | 2022 | 35750 |  | Cum Res fund (REET)
II. Storm water |  |  |  |  | 346932 | 0
2.1 | Storm Water System Improvements (SCMP CIP-18) | Install storm water conveyance along SE 27th St from 104th SE to western end of road. (SCMP CIP-18) |  | 2020-2021 | 250000 |  | Grant, matching funds from Cum Res fund
2.2 | Storm Water System Improvements (SCMP CIP-14) | Slurry Deposited 10-feet downstream of CB #637 and Hole in the Pipe 31-feet Downstream of CB #637 |  | 2021-2024 | 10670 |  | Cum Res fund (REET)
2.3 | Storm Water System Improvements (SCMP CIP-15) | Pipe is Cracked 49-feet downstream of CB #674 and Debris 236-feet downstream of CB #674 |  | 2021-2024 | 10340 |  | Cum Res fund (REET)
2.4 | Storm Water System Improvements (SCMP CIP-16) | Pipe is Broken 76-feet Upstream of CB #672 |  | 2021-2024 | 14630 |  | Cum Res fund (REET)
2.5 | Storm Water System Improvements (SCMP CIP-10) | Pipe is Broken between CBs #529 and 543 |  | 2021-2024 | 17358 |  | Cum Res fund (REET)
2.6 | Storm Water System Improvements (SCMP CIP-19) | 107th Ave SE-South of SE 28th Street. Localized Flooding in the Roadway Shoulder |  | 2021-2024 | 11000 |  | Cum Res fund (REET)
2.7 | Storm Water System Improvements (SCMP CIP-13) | Pipe is Broken Between CBs #587 and #595. Pipe is Reverse-Sloped |  | 2021-2024 | 12804 |  | Cum Res fund (REET)
2.8 | Storm Water System Improvements (SCMP CIP-21) | Pipe Between CBs #701 and #704. Pipe is Reverse-Sloped |  | 2021-2024 | 20130 |  | Cum Res fund (REET)
III. Water Department | [5 empty] | 0
3.1 | 104th Water Supply Pipe Replacement (section) | Replace 104th supply line pipe from SE 27th to SE 28th (4" A/C line) |  | 2023 | 125000 |  | Water fund
3.2 | 107th Water Supply Pipe Replacement (section) | Replace 107th supply line pipe from SE 29th to SE 28th (4" A/c line) |  | 2024 | 40000 |  | Water fund
3.3 | SE 29th Water Supply Line | Install new supply line along SE 29th from 103rd Ave SE to South Beach (for water quality improvement) |  | 2025 | 25000 |  | Water fund
IV. ROW Improvements |  |  |  |  | 70000 | 0
4.1 | 108th Ave SE Right of Way | Landscape design and implementation of landscaping, including extension of retaining wall |  | 2020-2022 | 60000 |  | Cum Res fund (REET)
4.2 | 102nd Ave SE path extension | Move 102nd path leading to SE 28th Pl (South Beach Road) from private property to Town right-of-way |  | 2020 | 10000 |  | Cum Res fund (REET)
Investments Pending Evaluation | [5 empty] | 0
| 104th/105th Traffic Calming | Improvements for 104th/105th for speed and cut through traffic mitigation |  | tbd | tbd
| Pathway Lighting | Design and implementation of landscaping lighting for town paths |  | tbd | tbd
| Town hall / Community Center | Needs assessment, design, and development of town hall / community center |  | tbd | tbd
| Security System | Design and implementation of security system for entrances to town, possibly other key locations |  | 2020-2022 | 15000 |  | Criminal Justice fund